Plan for Joint Position Statement on Response to Intervention (RTI) in Early Childhood

Goals

- Develop and validate a joint DEC/NAEYC/NHSA1 position statement on RTI in early childhood in accordance with the administrative and board policies of all three organizations.

- Provide opportunities in multiple formats for stakeholder groups to share information and access resources related to the joint position statement.

Steering Committee

| DEC |  |
| --- | --- |
| Sarah Mulligan | Executive Director |
| NAEYC |  |
| Jerlean Daniel | Executive Director Designate |
| Peter Pizzolongo | Senior Director, Professional Development |
| NHSA |  |
| Angela Smith | Professional Development Director |
| NPDCI2 |  |
| Virginia Buysse (Co-Chair) | Senior Scientist, University of North Carolina at Chapel Hill (UNC-CH) |
| Camille Catlett (Co-Chair) | Investigator, UNC-CH |
| Heidi Hollingsworth | Research Associate, UNC-CH |

National Experts

| Sue Bredekamp | Consultant |
| --- | --- |
| Judith J. Carta | University of Kansas |
| Marijata Daniel-Echols | High Scope Educational Research Foundation |
| Douglas H. Clements | University at Buffalo |
| David K. Dickinson | Vanderbilt University |
| Linda M. Espinosa | University of Missouri |
| Mary Louise Hemmeter | Vanderbilt University |
| Marilou Hyson | Consultant |
| Gail Joseph | University of Washington |
| Scott McConnell | University of Minnesota |
| Rollanda O’Connor | University of California, Riverside |
| Ellen Peisner-Feinberg | UNC-CH |
| Carolyn Webster-Stratton | University of Washington |

Work Groups

| DEC |  |
| --- | --- |
| Bill Brown | Faculty (SC) |
| Samtra Devard | Parent (DE) |
| Jim Lesko | 619 Coordinator/State EC Administrator (DE) |
| Donna Nylander | Early childhood administrator (IL) |
| NAEYC |  |
| TBA |  |
| NHSA |  |
| TBA |  |

Listening Sessions

Purpose: To obtain input on key issues related to RTI in early childhood from stakeholder groups and to use this information to inform the development and validation of the joint position statement.

| Date | Listening Sessions |
| --- | --- |
| December 8, 2009 | OSEP3 National Early Childhood Conference, Washington DC |
| May 6, 2010 | NHSA Annual Conference, Dallas TX |
| May 18-19, 2010 | National Inclusion Institute, Chapel Hill NC |
| June 6-9, 2010 | NAEYC National Institute for Early Childhood Professional Development, Phoenix AZ |
| July 19-21, 2010 | OSEP Project Directors’ Conference, Washington DC |
| October 14-17, 2010 | DEC Annual Conference, Kansas City MO |
| November 3-6, 2010 | NAEYC Annual Conference, Anaheim CA |

Timeline

| Date Range | Joint Process | Methodology |
| --- | --- | --- |
| September 2009 – January 2010 | Engage organizational partners (DEC, NAEYC, NHSA) | Obtain approval for process and timeline from DEC, NAEYC, and NHSA governance boards Identify key national experts (n=13) |
| February – June 2010 | Get input from key national experts Develop initial draft | Gather existing source materials on RTI in early childhood Convene key national experts to identify key issues and source material for the development of a joint position statement. Continue discussion and input via electronic platform on the NPDCI website Use input from key national experts as the basis for a an initial product (e.g., a policy alert) Establish work group – 4 DEC members, 4 NAEYC members, 4 NHSA members |
| June – August 2010 | Provide briefing for work group members Support input on draft position statement via electronic platform | Convene work group members. Provide background and briefing materials developed by national experts to support their work. Create an electronic platform on the NDPCI website for discussion by the joint DEC-NAEYC-NHSA work group and the key national experts Facilitate discussion Coordinate session on joint position statement at NHSA National Training Conference and NAEYC Professional Development Institute Generate initial draft position statement |
| September – December 2010 | Share draft position statement with targeted national groups and national experts via electronic platform | Obtain input from DEC, NAEYC, and NHSA re: groups to target for input (e.g., DEC subdivisions, 619 Coordinators, NAEYC affiliates, Head Start Collaboration directors) Create an electronic platform on the NPDCI website for discussion of draft position statement with targeted group members and national experts Facilitate discussion Revise draft to incorporate input Request approval to move forward to national review from all three boards Coordinate sessions on joint position statement at DEC and NAEYC annual meetings |
| January – March 2011 | National validation | Invite national organizations and individuals to review, provide input, and discuss the joint position statement via an electronic platform on the NPDCI website. Share the invitation to provide input with diverse audiences, including NAEYC affiliates and learning communities, DEC subdivisions and committees, Head Start networks, and other audiences |
| March – April 2011 | Incorporate input | Compile and incorporate input from national validation in final draft |
| May – June 2011 | Submit final draft for approval by DEC, NAEYC, and NHSA boards | Request DEC Executive Board approval at April CEC meeting Request NAEYC Governing Board approval at April meeting Request NHSA Executive Board approval at May meeting |
| July – Aug 2011 | Prepare position statement for release and distribution | Create final formats for web posting and dissemination |
| September – December 2011 | Distribute joint position statement | Submit articles to DEC, NAEYC, and NHSA journals and publications Coordinate presentations at DEC (October), NAEYC (November), and NHSA (September) Create a permanent landing pad for position statement and related products, resources, and examples |

_________________________________________________________________________________

1 Division for Early Childhood/National Association for the Education of Young Children/National Head Start Association

2 National Professional Development Center on Inclusion, Frank Porter Graham Child Development Institute, UNC-CH

3 Office of Special Education Programs