NJ Early Intervention System (NJEIS) CORRECTIVE ACTION PLAN (CAP)

TO ADDRESS SYSTEMIC NONCOMPLIANCE

| NJEIS Contact | Agency Name | Date CAP Requested | Date CAP Due to NJEIS |
| --- | --- | --- | --- |
|  |  | 10-6-2011 | 11-1-2011 |

- Areas of Noncompliance

- Failure to implement service coordination responsibilities

“Specific service coordination activities.”

Service coordination activities include – Facilitating the development of a transition plan to preschool services, if appropriate (34 CFR 303.23(b) (7)).

- Failure to meet transition timelines

Notifying the local education agency for the area in which the child resides that the child will shortly reach the age of eligibility for preschool services and; discuss the appropriate services that the child may receive, establish a transition plan and ensure coordination on transition matters. (34 CFR 303.148(b) (1-4)).

- Finding/Supportive Evidence:

According to SPOE data and the SCU Inquiry Report submitted in June, 2011, 95% of the children whose third birthday was in February, March and April, 2011 had transition steps in their IFSP.  However, 5% of the children whose third birthday was in February, March and April 2011 were missing transition steps in their IFSP.

According to SPOE data and the SCU Inquiry Report submitted in June, 2011, 90% of the children whose third birthday was in February, March and April, 2011 had written notification to the LEA in their record.  However, 10% of the children whose third birthday was in February, March and April 2011 were missing written notification to the LEA in their record.

Corrective Actions:  Complete the following to detail the actions your agency will take to correct the noncompliance in a timely manner.  This CAP must be submitted to NJEIS for approval by November 1, 2011.  All noncompliance must be corrected by June 30, 2012 in accordance with the evidence of change statements provided below.

| Corrective Action | Strategies | Who is responsible? | Timeline |
| --- | --- | --- | --- |
| Development/Revisions to Service Coordination Unit (SCU) Procedures |  |  |  |
| Infrastructure/Staffing |  |  |  |
| Provisions of Training |  |  |  |
| Provision of Technical Assistance |  |  |  |
| Changes to Supervision |  |  |  |

| Required Evidence of Change | Date To Be Completed |
| --- | --- |
| On each subsequent month, document the current status of the Transition Steps and Written notification to the LEA for each reporting month. Baseline 90% compliance The required targets for compliance are: As of 11/30/11 for children who turn 3 in February 2012 95% compliance Report due 11/30/11 As of 12/30/11 for children who turn 3 in March 2012 100% compliance Report due 12/30/11 No evidence of systemic non-compliance | Monthly Summary Reports submitted to NJEIS beginning November 30,2011 |

Signatures of individuals completing report 					Agency and Title					Date

CAP to be submitted by November 1, 2011 to                           , EIS Monitoring Officer

Signature, Title and Date the report was accepted by NJEIS

|  | EIS Monitoring Officer New Jersey Early intervention System |  |
| --- | --- | --- |