## Sheet1
NC Early Intervention (Infant-Toddler) Program
Integrating Child Outcomes with IFSP Process
Stages of Implementation
2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01
EXPLORATION PHASE | [5 empty] | INSTALLATION PHASE | [5 empty] | INITIAL IMPLEMENTATION STAGE |  |  |  |  | FULL IMPLEMENTATION STAGE
Articulate Desired Changes/Results | [5 empty] | Secure Leadership Support | [5 empty] | Implement Training & TA |  |  |  |  | Maintain & Improve Skills and Practice
Compare Approaches | [5 empty] | Develop a Communication Plan/Message Materials | [5 empty] | Implement an Integrated IFSP and COM Process |  |  |  |  | Maintain Infrastructure for Data Collection and Monitoring
Explore Implementation | [5 empty] | Build Implementation Team | [5 empty] | Support Reflection & Use of Feedback Loops |  |  |  |  | Assess Implementation of Integrated Process
Conduct Public Awareness | [5 empty] | Determine System Supports | [5 empty] | Adapt and Adjust Infrastructure to Support Practices |  |  |  |  | Create Organizational Structures to Support Integrated Process
Move On To Installation | [5 empty] | Build Training & Technical Assistance Capacity | [5 empty] | Evaluate Fidelity and Quality of Initial Efforts |  |  |  |  | Take Action to Ensure Sustainability
[6 empty] | Develop an Implementation Plan | [5 empty] | Make Changes to Support Sustainability
Move on to Initial Implementation
NC ITP Child Outcomes Workgroup | [5 empty] | Review data/plans with NC EI State Program Leadership | [5 empty] | Complete initial Training/TA |  |  |  |  | Define roles/responsibilites for entire Local Program (CDSA) Staff
NC ITP QI Unit | [5 empty] | Interviews with Leadership at Local EI Programs (CDSAs) | [5 empty] | Evaluate Training/TA |  |  |  |  | Training
NC ITP Data Team | [5 empty] | Check in with ECO Center to inform them of plans to Implement | [5 empty] | Revise Training/TA Materials Based on Evaluation Results |  |  |  |  | Refresher Trainings
How? Why? Who? Tool | [5 empty] | Discussion with Part B Preschool Partners | [5 empty] | Ongoing Coaching/Mentoring |  |  |  |  | Supervision, Coaching, and Mentoring
Participate in Learning Community | [5 empty] | Consultation with NC Early Learning Network | [5 empty] | Note Most Effective Support Approaches |  |  |  |  | Feedback Loops
Explore Resources From Other States | [5 empty] | Review Materials Developed for Families by Other States | [5 empty] | Assess Additional/Future Needs of Initial Implementation Teams |  |  |  |  | Share Results of Feedback
Scale for Assessing State Implementation of a COM System | [5 empty] | Use Communication Materials Dev for Professionals by ECO Center & Other States | [5 empty] | Develop Additional Training/TA Materials for Initial Implementation Team |  |  |  |  | Adapt Monitoring Systems as Needed
ECTA Center IFSP Training | [5 empty] | Draft Brochure for Families | [5 empty] | Create materials for CDSA-Wide and Statewide Implementation |  |  |  |  | Include Fidelity Measures as Part of Performance Assessment
IFSP Outcomes Integration Tool | [5 empty] | Develop Orientation Presentation and Packet for Early Implementers | [5 empty] | Initial Implementation |  |  |  |  | Create Various Reporting Capabilities to Help Local Programs Use Data
IFSP Flow Chart | [5 empty] | Draft Documents/Tools for Communication and Get Local Staff Feedback | [5 empty] | Feedback Loop |  |  |  |  | Analyze Data/Information for Decisions About Statewide Implementation
Integrating COM/IFSP Process Overview | [5 empty] | Create Local Implementation Teams for Early Implementation Sites | [5 empty] | Evaluation of Initial Implementation |  |  |  |  | Review/Update Policies/Procedures
NC ITP Leadership Team (Local Program Directors) | [5 empty] | Provide Orientation & Packet & Discuss Role of Implementation Team Members | [5 empty] | Child Outcomes Fidelity Self Assessment (Complete Again) |  |  |  |  | Revise Record Review Tool to Include Integration
Include info in NC ITP Training on New/Revised IDEA Regs | [5 empty] | Consider Stakeholder Group Membership and Input | [5 empty] | IFSP Outcomes Integration Tool (Complete Again) |  |  |  |  | Use Tool to Assess Implementation
Name for Change Initiative | [5 empty] | Child Outcomes Fidelity Self-Assessment | [5 empty] | Early Implementers Assessment/Planning Tool (Complete Again) |  |  |  |  | Share Data with Stakeholders
Revisit Commitment from Leadership Team | [5 empty] | Brainstorm with Local Implementation Teams Necessary Initial Changes | [5 empty] | Discuss Process/Evaluation Results with State Leadership Team |  |  |  |  | Reduce Barriers to Implementation
Choose Local Programs to be Early Implementers | [5 empty] | Early Implementers Assessment/Planning Tool | [5 empty] | Adapt/Adjust TA Support from State Office as Needed |  |  |  |  | Feedback Loops on What Will/Won't Change & Why
[6 empty] | List Tools, Guidance, etc.to be Developed/Revised for Initial Implementation | [5 empty] | Revise Materials, Forms, Process, etc. as Needed |  |  |  |  | Share Data to Expand Buy-In
[6 empty] | Secure Funding for Training/TA and Development of Print Materials | [5 empty] | Anticipate Changes to Statewide Policies, Procedures, Forms, etc. |  |  |  |  | Review/Adjust Support Needed to Sustain Statewide
[6 empty] | Arrange/Reserve Time for Research, Consultation, & Contacts/TA visits | [5 empty] | Consider Contracts/Agreements that Need to Be in Place Statewide |  |  |  |  | Revise Training/TA Over Time to Support New & Improved Practices
[6 empty] | Local Program (CDSA) Training/Guidance Needs Assessment | [5 empty] | Adapt/Adjust Fidelity and Quality Measures and Tools |  |  |  |  | Use Data to Make Decisions About Program Improvement
[6 empty] | Review Examples of Trng/TA Materials w/CDSA Implementation Teams | [5 empty] | Provide Information/Data to Stakeholders
[6 empty] | Gather Input from Rest of Local Program (CDSA) staff onTrng/TA Needs | [5 empty] | Training/TA
[6 empty] | Create Evaluation for Training/TA | [5 empty] | Provide Information to Extended List of Stakeholders
[6 empty] | Initial Overview & Plan for Early Implementers | [5 empty] | Integrate Evaluation Criteria into Ongoing Monitoring Efforts
Local Program (CDSA) Communication & Next Steps Planning
Communicate Overview & Initial Plan with Rest of CDSA & Get Feedback
Evaluation Plan for Implementation
Identify Specific Opportunities to Review Feedback
Review & Make Adjustments to Plans, Tools, Assessments, etc.